## Gantt Chart
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Start Date in Number Form | 43116 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Capstone Project | 2018-01-16 | 2018-05-03 | 107 | 70 | 37
Phase I | 2018-01-16 | 2018-02-12 | 27 | 27 | 0
Project Propsal | 2018-01-25 | 2018-02-01 | 7 | 7 | 0
Project Abstract | 2018-02-09 | 2018-02-16 | 7 | 7 | 0
Project Presentation 1 Deliverables | 2018-02-05 | 2018-02-12 | 7 | 7 | 0
Project Presentation 1 | 2018-02-12 | 2018-02-17 | 5 | 5 | 0
Phase II | 2018-02-17 | 2018-03-19 | 30 | 30 | 0
Project Interim Report | 2018-02-23 | 2018-03-09 | 14 | 14 | 0
Project Presentation 2 Deliverables | 2018-03-12 | 2018-03-19 | 7 | 7 | 0
Project Presentation 2 | 2018-03-19 | 2018-03-24 | 5 | 5 | 0
Phase III | 2018-03-24 | 2018-05-03 | 40 | 3 | 37
Project Final Report | 2018-04-02 | 2018-04-16 | 14 | 0 | 14
Project Poster Draft | 2018-04-09 | 2018-04-16 | 7 | 0 | 7
Project Final Poster | 2018-04-13 | 2018-04-20 | 7 | 0 | 7
Poster Day | 2018-04-18 | 2018-04-25 | 7 | 0 | 7
1 Minute Video | 2018-04-24 | 2018-05-01 | 7 | 0 | 7
Exit Survey | 2018-04-24 | 2018-05-01 | 7 | 0 | 7
Capstone Project | 2018-01-16 | 2018-05-03 | 107 | 70 | 37
Toolset & Material Familiarization | 2018-01-21 | 2018-02-04 | 14 | 14 | 0
Distribution of Work | 2018-01-28 | 2018-02-04 | 7 | 7 | 0
Assembler | 2018-02-04 | 2018-03-04 | 28 | 28 | 0
Memory & Registers | 2018-02-04 | 2018-03-04 | 28 | 28 | 0
File Editor | 2018-02-04 | 2018-03-04 | 28 | 28 | 0
Splash and GUI | 2018-02-04 | 2018-03-04 | 28 | 28 | 0
Integration & Debugging | 2018-02-25 | 2018-03-25 | 28 | 28 | 0
Extension: Simulator | 2018-03-18 | 2018-04-15 | 28 | 9 | 19
Base: RV32I, RV64I; Extension: M, A, F, D | 2018-03-18 | 2018-04-15 | 28 | 9 | 19
Final Integration & Debugging | 2018-04-01 | 2018-04-15 | 14 | 0 | 14
Capstone Project | 2018-01-16 | 2018-05-03 | 107 | 70 | 37

## Notes
Features of Project
Assembler
Parse and handle command chunks
Error handling invalid command chunks
Line-by-line interpretation speed is altered by user setting
Abide by base and extensions selected
Debugger
Assembler
File Editor
Auto-fill text based on valid instructions and previousely used user defined variables
Save, open, close, temporary file(s)
Hanlding muliple open files
Terminal
Display messages (error, program)
User I/O
Clear history button/option
Base Selection
RV32I
RV64I
RV32E
RV64E
Extensions
M :: Integer Multiplication & Division
A :: Atomic Instructions
F :: Single Precision Floating-Point
D :: Double Precision Floating-Point
Registers
Quantity changes with Base
Values altered by command strings
Coprocessors
Vector
Memory
Text section
Data section
Hex display
Octal display
Deci display
ASCII display
Endianness Toggle
Little to Big
Big to Little
User Command Bar
File
New
Open, Close
Save, Save As
Print/Export
Edit
Undo, Redo
Copy, Cut, Paste
Run
Compile
Assembly File Dump
Settings
Base Selector
Extension Selector
Tools
Instruction Statistics
IEEE 754 Converter
Help
Glossary
List of Instructions by Extension
Real
Pseudo
About program
Liscense
Acknowledgements
Programmers
University
Splash
Show first, then launched program GUI
Contain License information and program name
Have status bar of loading or launch count down
Control Bar
Have instruction step forward, step back
Compile and run
Instruction interpretation speed
Open source icon
Vectorized icons if possible
Record where icon are taken from to proper citation
Points of Interest
File Chooser
https://docs.oracle.com/javafx/2/ui_controls/file-chooser.htm
Random Point
Display current bese and extensions on status bar
Poster format is allowed to be altered (but keep the title bar the same)
60 second video can be a pitch or a demo of the project

## DoW
Tasks | Skyler | Arjun | Alejandro | Raj
Administration | PoC
Technical | Assembler | File Editor | Splash and GUI | Memory & Registers
System Bar
Control Bar
Sub-Menu